## Sheet1
Risk ID | Date Identified | Asset/System | Threat Description | Vulnerability Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Rating | Existing Controls | Treatment Plan | Risk Owner | Target Remediation Date | Status | Residual Risk Acceptance
R-2024-001 | 2024-02-15 | HR Database | Unauthorized access attempt detected via brute force | Weak password controls in HR system | 4 | 4 | 16 | High | MFA enabled, IDS monitoring | Enforce password complexity, regular audits | IT Security Manager | 2024-03-15 | Closed | No
R-2024-002 | 2024-09-10 | Corporate Email | Phishing emails targeting employees | Lack of employee phishing awareness training | 3 | 3 | 9 | Medium | Spam filter, email gateway security | Conduct phishing simulation training | IT Security Manager | 2024-10-15 | In Progress | Pending
R-2025-001 | 2025-03-05 | Cloud Storage (AWS S3) | Misconfigured S3 bucket exposing confidential data | Bucket policy incorrectly set to public read access | 5 | 5 | 25 | Critical | S3 encryption enabled, CloudTrail logging | Restrict bucket access, implement IAM least privilege | Cloud Engineer | 2025-03-20 | Open | No
R-2025-002 | 2025-07-22 | Vendor SaaS Platform | Vendor outage affecting customer-facing services | No redundant vendor service contract in place | 3 | 4 | 12 | Medium | Vendor SLA with partial redundancy | Evaluate secondary vendor, update DR strategy | Operations Manager | 2025-08-15 | In Progress | Yes