## Evidence actions
Priority | Requirement # | Department | Requirement | Tracker status | Audit-period evidence requested | Action / responsible owner | Target folder/path | Completion status | Evidence link/reference | Owner confirmation / notes
1 - Evidence/owner action | 1 | HR | Reviewed organiation chart. how is it made available to staff? | Available Baseline (Needs Refresh) | Updated Org Chart reflecting current team as of 2025-2026; screenshot showing publication on Zoho People. | HR: Refresh org hierarchy, upload to Zoho People, take screenshot. | 02_HR_and_People/1 - Organisation Chart.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 2 | HR | Vision /Mission | Available Baseline (Needs Refresh) | Employee Handbook (v2.0) containing Vision & Mission; induction PPT used during audit period. | HR: Share updated handbook and sample induction presentation deck. | 02_HR_and_People/4 - HR Employee Handbook.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 3 | HR | Name HRMS tool used by HR department if any | Operational / Implemented | Screenshot of Zoho People admin dashboard showing employee active roster, attendance, and leave management. | HR: Capture screenshot of Zoho People portal overview. | 02_HR_and_People/Screenshots/Zoho_People_Dashboard.png | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 4 | HR | HR Policies and procedures covering all aspects and how are th policies made available to staff? | Operational / Implemented | Screenshot of Zoho People 'Files / Policies' section demonstrating staff access to company policies. | HR: Capture screenshot of policies published inside Zoho People. | 02_HR_and_People/Screenshots/Zoho_People_Policies_View.png | Open - evidence/owner confirmation required
1 - Evidence/owner action | 5 | HR | Code Of Condut Sign off- new hires and existing employes annually both | Action Required (Collect Period Samples) | Signed Code of Conduct / NDA attestations for 2-3 new hires joined in Oct 2025 - Sep 2026, plus annual employee sign-off logs. | HR: Extract signed Code of Conduct acknowledgments for period hires. | 02_HR_and_People/3 - Supporting Documents/Code_of_Conduct_Signoffs_2025_2026/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 6 | HR | Information and communication- HR head meetings with top mgt and team | Action Required (Collect Period Samples) | Minutes / calendar invite / email record of HR Head review meetings with leadership during the audit period. | HR: Provide meeting notes / summary of quarterly leadership HR reviews. | 02_HR_and_People/Meeting_Minutes/HR_Leadership_Meetings_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 7 | HR | Sample of tickets if any ticketing system used for grievance./complain | Available Framework (Declare Period Tickets) | Grievance register / ticket log for 2025-2026 or formal management declaration of zero grievances raised during period. | HR: Maintain zero grievance declaration or grievance log. | 02_HR_and_People/Grievance_Register_2025_2026.xlsx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 8 | HR | RESOURCE PLANNING | Action Required (Collect Period Notes) | Resource planning email / spreadsheet showing headcount forecasting and hiring plan for 2025-2026. | HR: Provide resource planning discussion email/doc. | 02_HR_and_People/Resource_Planning_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 9 | HR | Job descriptions (JD) | Available Baseline (Sample Roles) | Documented Job Descriptions (JDs) for roles hired during the audit period (e.g. Software Engineer, QA, DevOps). | HR: Provide 2-3 sample JDs for active job postings during period. | 02_HR_and_People/Job_Descriptions_2025_2026/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 10 | HR | Onboarding | Action Required (Collect Period Samples) | Complete onboarding dossier for 2-3 sample employees hired between Oct 1, 2025 and Sep 30, 2026 (Offer letter, Appointment letter, BGV report, signed NDA, signed Code of Conduct, technical evaluation). | HR: Gather full onboarding packets for 2-3 sample new hires. | 02_HR_and_People/3 - Supporting Documents/Onboarding_Samples_2025_2026/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 11 | HR | Training | Action Required (Collect Period Samples) | Annual Information Security & Privacy awareness training attendance log, training presentation deck, and employee quiz scores for 2025-2026. | HR/IT: Conduct/record annual security training log for all staff. | 02_HR_and_People/Security_Training_Log_2025_2026.xlsx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 12 | HR | Performance Appraisals | Action Required (Collect Period Samples) | Completed annual performance evaluation forms / appraisal records conducted in 2025-2026 (sample 2-3 employees). | HR: Provide 2 completed performance evaluation records. | 02_HR_and_People/Performance_Appraisals_2025_2026/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 13 | HR | EXIT FORMALITIES | Action Required (Collect Period Samples) | Exit checklist, department clearances (duly signed), and last working date communication for 1-2 exits during 2025-2026. | HR: Provide exit clearance checklist for sample leaver. | 02_HR_and_People/Exit_Clearance_Samples_2025_2026/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 14 | ADMIN | Office Entry is restricted … How? Employee id card, acess card | Available Baseline (Needs Photo Proof) | Photos of office biometric / RFID access control reader and employee ID badge template. | Admin: Provide clear photos of entry biometric door reader. | 03_Admin_and_Physical_Security/01_Physical_Security/6 - Presence of CCTV, biometrics, smoke detectors.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 15 | ADMIN | CCTV | Available Baseline (Needs Refresh) | Screenshot of CCTV NVR/DVR storage dashboard proving 30-90 days continuous footage retention. | Admin: Screenshot CCTV storage recording settings and capacity. | 03_Admin_and_Physical_Security/01_Physical_Security/CCTV_Retention_Proof.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 16 | ADMIN | Security Guard | Available Baseline | Security guard deployment log or office building commercial lease agreement covering 24/7 security. | Admin: Provide building security contract or guard register. | 03_Admin_and_Physical_Security/02_Admin_Facility/Building_Security_Agreement.pdf | Open - evidence/owner confirmation required
1 - Evidence/owner action | 17 | ADMIN | Visitor Register | Action Required (Collect Period Register) | Physical visitor register log sheets showing entry/exit records and visitor badge issuance for 2025-2026. | Admin: Provide scanned pages / photo of filled visitor log. | 03_Admin_and_Physical_Security/02_Admin_Facility/7 - Visitor Register.xlsx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 18 | ADMIN | Server room | Direct Proof (Cloud Native Declaration) | Formal declaration / network rack photo: Zediant operates 100% on AWS Cloud; no on-premise production server room exists. | IT/Admin: Re-confirm cloud-only architecture statement. | 03_Admin_and_Physical_Security/01_Physical_Security/Cloud_Native_Infrastructure_Declaration.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 19 | ADMIN | Environmental Controls Maintenance Checklist | Available Baseline (Needs Current Tags) | Photos of fire extinguishers showing valid maintenance inspection tags for 2025-2026, plus first aid kits. | Admin: Take photos of annual extinguisher service tags. | 03_Admin_and_Physical_Security/01_Physical_Security/Fire_Extinguisher_Inspection_Photos.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 20 | ADMIN | Fire drill | Action Required (Collect Period Drill) | Building / office fire drill report or evacuation exercise conducted during the audit period. | Admin: Obtain building fire drill report / memo. | 03_Admin_and_Physical_Security/01_Physical_Security/Fire_Drill_Report_2025_2026.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 21 | ADMIN | UPS, DG | Available Baseline (Needs Period AMC) | Annual service maintenance report / receipt for UPS and DG power backup covering 2025-2026. | Admin: Provide current UPS AMC invoice / inspection sheet. | 03_Admin_and_Physical_Security/02_Admin_Facility/10 - AMC Register.xlsx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof |  | GOV | Security Certifications | Available Baseline | Copy of the 2025 SOC 2 Type 2 Audit Report issued by previous auditor. | Management: Keep previous SOC 2 report available for vendor review. | 04_Governance_and_Finance/02_Risk_and_Compliance/SOC2_Type2_Report_2025.pdf | Open - evidence/owner confirmation required
1 - Evidence/owner action |  | GOV | MRM / CISO Meetings | Action Required (Collect Period Minutes) | Minutes of Management Review Meeting (MRM) and CISO security committee meetings held during 2025-2026. | CISO/Management: Provide meeting minutes of annual security review. | 04_Governance_and_Finance/02_Risk_and_Compliance/MRM_Minutes_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof |  | GOV/POLICY | ISMS policies/Procedure | Staged & Complete (Ready for Stamp) | Full set of 40 policies reviewed, approved, and stamped for effective period October 1, 2025 – September 30, 2026. | CISO: Formal policy approval memo and annual review sign-off. | 01_Policies_and_Procedures/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 1 | customer success | Customer SLA monitoring | Available Baseline (Sample SLA) | Sample customer SLA performance report / uptime dashboard (99.9% availability) shared with client in 2025-2026. | CS/Ops: Provide 1 sample customer uptime / SLA report. | 07_Client_and_Vendor/Customer_SLA_Reports_2025_2026/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 2 | customer success | cadence calls with clients weekly/monthly | Action Required (Collect Period Notes) | Calendar invite / email minutes of periodic client cadence / review meetings held during 2025-2026. | CS: Provide 1-2 client cadence meeting notes. | 07_Client_and_Vendor/Client_Cadence_Minutes_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 3 | customer success | customer complains via ticketing systm or email | Available Baseline (Declare Period Tickets) | Client complaints log for 2025-2026 or formal declaration of zero client complaints during audit period. | CS: Provide updated complaints register showing resolution / zero complaints. | 07_Client_and_Vendor/4 - Client Complaints Register.xlsx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 4 | customer success | Reporting of incidents to external users | Available Baseline (Sample Notice) | Sample external incident communication / scheduled maintenance notification sent to clients during 2025-2026. | IT/CS: Provide sample client maintenance notification email. | 07_Client_and_Vendor/Client_Maintenance_Notices_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 5 | customer success | Creating client user accounts on cloud application-customer onboarding and training | Available Baseline (Sample Ticket) | Client onboarding workflow / sample ticket showing creation of client tenant accounts and user access provisioning. | CS/IT: Provide sample client tenant provisioning record. | 07_Client_and_Vendor/Client_Account_Creation_Evidence_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 1 | website | website | Available Baseline (Live Verification) | Screenshots of live Zediant website showing active Privacy Policy, Security terms, updated service descriptions, and Copyright © 2026. | Marketing/IT: Capture full-page screenshot of zediant.com with footer. | 06_Privacy_and_Data_Protection/Website_Privacy_and_Copyright_2026.png | Open - evidence/owner confirmation required
1 - Evidence/owner action | 1 | GOV/RISK | Risk | Available Baseline (Needs 2025-26 Update) | Updated Risk Register for 2025-2026 formally covering Fraud, Privacy, AI / LLM, and Technology infrastructure risks with mitigation scores. | CISO/Risk: Review risk register, add AI/Privacy rows, and re-stamp date. | 04_Governance_and_Finance/02_Risk_and_Compliance/2 - Risk Register- 2024_25.xlsx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 1 | GOV/IA | Internal Audit | Action Required (Generate Internal Audit) | Internal SOC 2 Audit schedule, completed Internal Audit report for 2025-2026, and minutes demonstrating management review of findings. | CISO/Consultant: Prepare and execute annual internal audit report. | 04_Governance_and_Finance/02_Risk_and_Compliance/Internal_Audit_Report_2025_2026.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 1 | GOV/FIN | MSA/SOW/Newsletter?weekly updates | Available Baseline (Sample Required) | 1-2 executed client MSA/SOW contracts from 2025-2026 containing Confidentiality, SLA, Data Security, and Escalation Matrix clauses. | Finance/Legal: Provide 1-2 active executed client MSAs. | 07_Client_and_Vendor/6 - Supporting Documents/1 - Client Service Agreement/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 2 | GOV/FIN | VENDOR | Available Baseline (Sample Required) | Filled vendor due diligence checklist for newly onboarded vendors during 2025-2026. | Finance/IT: Provide completed vendor checklist for 1 new vendor. | 07_Client_and_Vendor/6 - Supporting Documents/9 - Vendor Evaluation - Rating Form/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 3 | GOV/FIN | MGT-7, ROC filings /ITR /GST and outside india if any return to be filed whether filed timely? | Action Required (Collect Period Challans) | Filing acknowledgements / challans for GST monthly returns, Income Tax Return (ITR), and ROC / MGT-7 filed in 2025-2026. | Finance: Provide GST/ITR/ROC filing receipts for the audit period. | 04_Governance_and_Finance/01_Organization_Structure/Statutory_Filings_2025_2026/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 4 | GOV/FIN | minutes of board of directors meeting | Action Required (Collect Period Minutes) | Minutes of Board of Directors (BoD) meeting held during the 2025-2026 audit period. | Finance/Legal: Provide 1 set of BoD meeting minutes. | 04_Governance_and_Finance/01_Organization_Structure/1 - Supporting Documents/6 - Board Meeting/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 5 | GOV/FIN | insurance premium paid receipt | Action Required (Collect Current Policy) | Cyber Liability, E&O, and Commercial General Liability insurance policy schedule & premium payment receipt active for 2025-2026. | Finance: Provide renewed cyber insurance policy document. | 04_Governance_and_Finance/02_Risk_and_Compliance/8 - Supporting Documents/9 - Insurance Policy/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 6 | GOV/FIN | Frequency of meeting with other departments and leadership team | Action Required (Collect Period Notes) | Documentation / recurring calendar invites showing regular leadership meetings across HR, IT, Finance, and Ops. | Management: Share calendar screenshot of recurring leadership syncs. | 04_Governance_and_Finance/02_Risk_and_Compliance/Leadership_Meeting_Cadence_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 7 | GOV/FIN | access right for accounts team whether processes followed aptly? | Operational / Implemented | Screenshot of Zoho Books / accounting system user permissions showing role-based segregation of duties. | Finance: Capture screenshot of accounting role permissions. | 04_Governance_and_Finance/Screenshots/Zoho_Books_Access_Rights.png | Open - evidence/owner confirmation required
1 - Evidence/owner action | 1 | IT/devops | Network diagrams and system architecture diagram | Available Baseline (Needs Refresh) | Updated Cloud Architecture Diagram (AWS VPC, public/private subnets, ALB, ECS/EC2, RDS, WAF, KMS) reflecting 2025-2026 setup. | DevOps: Export current AWS network topology / architecture diagram. | 05_IT_and_DevOps/System_Architecture_Diagram_2025_2026.png | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 2 | IT/devops | Patch Management | Operational / Implemented | Patch management policy & automated patch deployment logs (AWS Systems Manager / OS unattended upgrades) during period. | DevOps: Provide screenshot of AWS patch compliance dashboard. | 05_IT_and_DevOps/Patch_Management_Evidence_2025_2026.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 3 | IT/devops | Asset Register | Available Baseline (Needs Refresh) | Comprehensive hardware and software asset register reviewed and reconciled as of 2025-2026. | IT: Reconcile laptop and SaaS inventory list. | 05_IT_and_DevOps/4 - Asset Register - 20260831.xlsx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 4 | IT/devops | System Access reviews/Firewall admin access/Client network Access/Physical access review periodically/Role based Access - Cloud/Local admin access/IAM on Azure/GCP/Sensitive areas Physical access Review periodically | Action Required (Conduct Quarterly Reviews) | Documented Quarterly User Access Reviews (AWS IAM, GitHub, Google/Zoho Workspace, Production DB) for Q1, Q2, Q3, Q4 with CISO sign-off. | IT/CISO: Document quarterly user access review sign-off sheets. | 05_IT_and_DevOps/Quarterly_Access_Reviews_2025_2026.xlsx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 5 | IT/devops | VAPT/wapt -infra, application, website? | Action Required (Provide Annual VAPT) | External Network & Web Application Penetration Testing (VAPT) Report conducted by certified vendor during Oct 2025 - Sep 2026 with closure sheet. | IT/DevOps: Share 2025-2026 VAPT report and vulnerability closure proof. | 05_IT_and_DevOps/7 - Supporting Documents/46 - Vulnerability Assessment and PEN Test/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 6 | IT/devops | Hardening standards | Available Baseline | Documented Hardening Standards for AWS AMI, Linux/Ubuntu containers, and employee workstations. | DevOps: Provide baseline hardening checklist. | 05_IT_and_DevOps/Hardening_Standards_Baseline.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 7 | IT/devops | MFA | Available Baseline (Needs Current Proof) | Current screenshots showing 100% MFA enforcement on AWS IAM, GitHub organization, and Zoho/Google Workspace. | DevOps/IT: Capture updated MFA enforcement screenshots across all portals. | 05_IT_and_DevOps/7 - Supporting Documents/32 - Multi-factor Authentication/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 8 | IT/devops | VPN connection to client environment and to company network for remote employees | Operational / Implemented | Screenshot of corporate VPN gateway configuration (OpenVPN / AWS Client VPN) showing encryption and MFA requirement. | DevOps: Screenshot VPN configuration and encryption cipher. | 05_IT_and_DevOps/Screenshots/VPN_Configuration_Proof.png | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 9 | IT/devops | Active Directory | Operational / Implemented | Screenshot of Centralized Identity Provider (IdP) user directory showing active user accounts and group memberships. | IT: Screenshot cloud identity user directory. | 05_IT_and_DevOps/Screenshots/IdP_User_Directory.png | Open - evidence/owner confirmation required
1 - Evidence/owner action | 10 | IT/devops | Encryption -data at rest and in transit | Available Baseline (Needs Current Proof) | Screenshots of AWS KMS key management (AES-256 for EBS, RDS, S3) and SSL/TLS certificates (TLS 1.2+ active on ALB/CloudFront). | DevOps: Take current AWS KMS and ACM certificate screenshots. | 05_IT_and_DevOps/7 - Supporting Documents/36 - Currently AWS KMS encryption configuration for data-at-rest and databases/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 11 | IT/devops | Account sharing prohibited/ No access to external users | Operational / Implemented | User listing demonstrating unique individual accounts across all systems; zero shared credentials. | IT: Confirm policy adherence and absence of shared accounts. | 05_IT_and_DevOps/Individual_Account_Verification.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 12 | IT/devops | Work in client environment only? | Operational / Implemented | Documented protocol / client contract clause stipulating engineering work occurs strictly in designated cloud environments. | DevOps: Provide standard developer protocol document. | 05_IT_and_DevOps/Client_Environment_Standard_Protocol.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 13 | IT/devops | Firewall | Available Baseline (Needs Current Proof) | Current AWS Security Group rule exports and AWS WAF inspection dashboard showing blocking of common web exploits. | DevOps: Export current AWS Security Group ingress rules. | 05_IT_and_DevOps/35 - firewall rules and configurations.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 14 | IT/devops | Printer | Operational (Paperless Cloud Office) | Statement and policy affirming 100% paperless cloud-first office; network printers restricted/disabled. | Admin/IT: Re-affirm paperless office protocol. | 05_IT_and_DevOps/Paperless_Office_Declaration.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 15 | IT/devops | Removable media prohibited-usb disabled | Available Baseline | Screenshot of Endpoint Management / Registry / Antivirus policy disabling USB mass storage devices. | IT: Capture screenshot of USB port restriction policy. | 05_IT_and_DevOps/24 - Control Of Removable Media Policy.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 16 | IT/devops | DLP Software | Operational / Implemented | Screenshot of cloud DLP controls (Google Workspace / Zoho external sharing restrictions). | IT: Screenshot cloud sharing restriction settings. | 05_IT_and_DevOps/DLP_Controls_Evidence.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 17 | IT/devops | Endpoint protection Antivirus installed | Available Baseline (Needs Current Proof) | Centralized Antivirus/EDR dashboard screenshot showing 100% active endpoints with current virus definitions updated daily. | IT: Provide fresh screenshot of AV centralized console with definition date. | 05_IT_and_DevOps/7 - Supporting Documents/41 - screenshot of the anti-virus software's current version number and definition level/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 18 | IT/devops | Backup and restoration | Available Baseline (Conduct Annual Drill) | Automated backup schedule configuration (AWS Backup / RDS snapshots) AND documented Backup Restoration Drill Report performed in 2025-2026. | DevOps: Perform and document database backup restoration test. | 05_IT_and_DevOps/Annual_Backup_Restoration_Drill_Report_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 19 | IT/devops | Reporting of virus detected | Operational / Implemented | Antivirus alert log or formal statement confirming zero malware/ransomware infections detected during the period. | IT: Provide AV detection log / zero malware declaration. | 05_IT_and_DevOps/Malware_Detection_Log_2025_2026.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 20 | IT/devops | Momitoring the infrastructure and cloud environment | Available Baseline (Needs Current Proof) | Current AWS CloudWatch / Datadog dashboard screenshots showing real-time CPU, RAM, disk, network metrics, and active alert alarms. | DevOps: Screenshot active CloudWatch monitoring alarms. | 05_IT_and_DevOps/7 - Supporting Documents/45 - maintain a capacity monitoring and alerts settings/ | Open - evidence/owner confirmation required
1 - Evidence/owner action | 21 | IT/devops | IT Help desk support ? If ticketing systemused share tickets | Action Required (Collect Period Tickets) | Sample IT helpdesk support tickets from Zoho Desk / Jira demonstrating ticket resolution and SLA compliance in 2025-2026. | IT: Export 2-3 resolved IT support tickets. | 05_IT_and_DevOps/Helpdesk_Tickets_2025_2026/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 22 | IT/devops | Incident management | Available Baseline (Declare Period Register) | Incident Register for 2025-2026, Root Cause Analysis (RCA) template, or signed declaration of zero high-severity security incidents during period. | IT/CISO: Maintain 2025-2026 incident register / zero incident declaration. | 05_IT_and_DevOps/2 - Incident Register - 20250902.xlsx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 23 | IT/devops | Change Management | Action Required (Collect Period PRs) | 2-3 sample Pull Requests (PRs) from GitHub showing developer branch, peer code review, automated CI test pass, and production deployment approval during 2025-2026. | DevOps: Export 2 approved GitHub PR screenshots. | 05_IT_and_DevOps/Change_Management_PR_Samples_2025_2026/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 24 | IT/devops | Communication of system changes to internal and external users | Available Baseline (Sample Notice) | Sample email / downtime banner / release notes communicating system upgrade or maintenance window in 2025-2026. | DevOps: Provide sample release note / downtime email. | 05_IT_and_DevOps/System_Release_Communications_2025_2026.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 25 | IT/devops | Audit reports, SOC reports /other compliance reports for key critical Vendors | Action Required (Download Current Reports) | Current SOC 2 Type 2 / SOC 3 reports and ISO 27001 certificates for critical vendors (AWS, Zoho, GitHub, Google Workspace) covering 2025-2026. | IT/DevOps: Download current SOC 2 reports from AWS Artifact, Zoho, and GitHub. | 05_IT_and_DevOps/Vendor_SOC_Reports_2025_2026/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 26 | IT/devops | BCP DR Plans | Available Baseline (Perform Period Drill) | Documented Disaster Recovery & Business Continuity Test Report conducted in 2025-2026 evaluating scenario, RTO, RPO, and management sign-off. | DevOps/CISO: Perform annual simulated DR failover drill and document results. | 05_IT_and_DevOps/DR_Test_Report_2025_2026.pdf | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 27 | IT/devops | ISP/swithces/ firewall / load balancer redundancy | Operational / Implemented | Documentation of AWS Multi-AZ auto-scaling redundancy and secondary commercial internet provider in office. | DevOps: Provide multi-AZ architecture note and secondary ISP bill. | 05_IT_and_DevOps/Redundancy_Documentation.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 28 | IT/devops | API | Operational / Implemented | Screenshot of AWS Secrets Manager / Parameter Store proving API keys and secrets stored securely with encryption and periodic rotation. | DevOps: Screenshot Secrets Manager dashboard. | 05_IT_and_DevOps/Screenshots/AWS_Secrets_Manager.png | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 29 | IT/devops | Audit logs | Operational / Implemented | Screenshot showing AWS CloudTrail enabled across all regions with logs forwarded to encrypted S3 bucket with 365-day retention. | DevOps: Screenshot CloudTrail log retention settings. | 05_IT_and_DevOps/Screenshots/CloudTrail_Retention_Settings.png | Open - evidence/owner confirmation required
1 - Evidence/owner action | 1 | PRIVACY | website:privacy policy | Available Baseline (Needs Refresh) | Updated website privacy policy specifying DPO contact, purpose, data categories, retention, third-party disclosure, and effective date. | Privacy Lead: Ensure website notice covers all 9 AICPA privacy elements. | 06_Privacy_and_Data_Protection/Website_Privacy_Notice_2025_2026.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 2 | PRIVACY | Privacy related training to staff and contractors | Action Required (Collect Period Logs) | Privacy training schedule and completion logs for new hires and existing employees conducted during 2025-2026. | HR/Privacy: Record annual privacy training sign-off sheet. | 06_Privacy_and_Data_Protection/Privacy_Training_Attendance_2025_2026.xlsx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 3 | PRIVACY | Privacy tracker | Available Baseline (Declare Period Register) | Privacy tracker / breach log for 2025-2026 confirming zero privacy incidents or intimation to data protection authorities. | Privacy Lead: Maintain privacy breach register. | 06_Privacy_and_Data_Protection/14 - Data Breach Register.xlsx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 4 | PRIVACY | A documented process exists for data subjects to request corrections, amendments, or additions to their personal information. | Operational / Implemented | Documented Data Subject Access Request (DSAR) procedure for data subjects to request correction, amendment, or addition. | Privacy Lead: Formalize DSAR procedure document. | 06_Privacy_and_Data_Protection/DSAR_Procedure_and_Form.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 5 | PRIVACY | All employees and sub contractors can view and edit personal information provisioned by sending a request to HR. | Operational / Implemented | Screenshot of Zoho People employee self-service profile allowing staff to view and edit personal information. | HR: Capture screenshot of employee self-service edit screen. | 06_Privacy_and_Data_Protection/Screenshots/Zoho_People_Self_Service.png | Open - evidence/owner confirmation required
1 - Evidence/owner action | 6 | PRIVACY | consent provided by prospective candidate for background verification check | Available Baseline (Sample Required) | Signed BGV consent forms from 2-3 candidate hires onboarded between Oct 1, 2025 and Sep 30, 2026. | HR: Provide 2-3 signed BGV consent letters. | 02_HR_and_People/3 - Supporting Documents/Background verification Consent/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 7 | PRIVACY | any privacy breach case reported during the audit period? If yes proof | Operational (Zero Incidents Declaration) | Formal declaration signed by CISO confirming zero privacy breaches occurred during the 2025-2026 audit period. | CISO: Sign zero privacy breach attestation. | 06_Privacy_and_Data_Protection/Zero_Privacy_Breach_Declaration.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 8 | PRIVACY | If personal information is collected from sources other than the individual, are such sources described in the privacy notice? | Operational / Implemented | Section in privacy notice describing categories of personal data collected from external or third-party sources. | Privacy Lead: Confirm clause in privacy notice. | 06_Privacy_and_Data_Protection/Website_Privacy_Notice_2025_2026.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 9 | PRIVACY | Is Notice is provided to data subjects (1) at or before the time personal information is collected or as soon as practical thereafter, (2) at or before the Company changes its privacy notice or as soon as practical thereafter, or (3) before personal information is used for new purposes not previously identified. | Operational / Implemented | Evidence of privacy notice provided at the point of data collection (candidate application form, website footer). | Privacy Lead: Provide screenshot of candidate application form privacy link. | 06_Privacy_and_Data_Protection/Notice_at_Collection_Evidence.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 10 | PRIVACY | Policies and procedures have been implemented to protect personal information from erasure or destruction during the specified retention period of the information. | Available Baseline | Enforcement of data retention controls preventing premature erasure of personal data during retention lifecycle. | Privacy Lead: Re-stamp policy date and verify enforcement. | 01_Policies_and_Procedures/22 - Data Retention and Disposal Policy.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 11 | PRIVACY | The organization has established a process to capture and manage requests for deletion of personal information, ensuring such data is identified and flagged for destruction in line with privacy objectives; however, no deletion requests had been received as of the audit date. | Operational (Zero Deletion Requests) | Process to manage Right to Erasure / Deletion requests, and signed log confirming zero deletion requests received to date. | Privacy Lead: Maintain deletion request log. | 06_Privacy_and_Data_Protection/3 - Data Retention and Disposal Log 2024_25.xlsx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 12 | PRIVACY | The MSA covers details on company's privacy requirements and is signed with the user Company. | Available Baseline (Sample MSA) | Client MSA / DPA executed in 2025-2026 containing comprehensive data privacy, GDPR, and DPDP compliance terms. | Legal/Finance: Provide sample MSA with privacy schedule. | 07_Client_and_Vendor/6 - Supporting Documents/1 - Client Service Agreement/ | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 13 | PRIVACY | Data subjects are informed (a) about the choices available to them with respect to the collection, use, and disclosure of personal information and (b) that implicit or explicit consent is required to collect, use, and disclose personal information, unless a law or regulation specifically requires or allows otherwise. | Operational / Implemented | Cookie consent management banner on website providing explicit opt-in/opt-out choices to data subjects. | Marketing/IT: Screenshot live website cookie consent banner. | 06_Privacy_and_Data_Protection/Cookie_Consent_Banner.png | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 14 | PRIVACY | A documented process exists for data subjects to request access to their personal information. | Operational / Implemented | Documented Data Subject Access Request (DSAR) workflow enabling individuals to request copies of personal data. | Privacy Lead: Maintain DSAR request channel. | 06_Privacy_and_Data_Protection/DSAR_Procedure_and_Form.docx | Open - evidence/owner confirmation required
2 - Confirm baseline/current proof | 15 | PRIVACY | Privacy data incidents are reported to management as and when they occur. | Operational / Implemented | Incident management escalation workflow ensuring privacy incidents are immediately escalated to executive management. | CISO: Confirm escalation workflow. | 01_Policies_and_Procedures/30 - Breach Response and Notification Procedure.docx | Open - evidence/owner confirmation required
1 - Evidence/owner action | 16 | PRIVACY | On an anuual basis Information security team performs risk and privacy assessments. | Action Required (Perform Annual Assessment) | Documented Annual Privacy Impact Assessment (PIA) / Privacy Risk Assessment conducted for 2025-2026. | CISO/Privacy Lead: Prepare and document 2025-2026 Privacy Impact Assessment. | 06_Privacy_and_Data_Protection/Annual_Privacy_Risk_Assessment_2025_2026.docx | Open - evidence/owner confirmation required

## Policy approvals
Policy # | Policy requirement | Tracker status | Action required | Owner | Actual approval reference/date | Evidence/location | Status
1 | disciplinary policy and procedure | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
2 | code of conduct policy | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
3 | rewards and recognition policy | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
4 | Vendor Management policy | Available - Staged (Needs Annual Review Stamp) | Re-stamp effective date to Oct 1, 2025, increment version to v2.0, management approval sign-off. |  |  |  | Open - owner review/approval required
5 | ISMS MANUAL. Information security policies and procedures as per ISMS | Available - Staged (Needs Annual Review Stamp) | Master ISMS document. Update review date to Oct 1, 2025, bump version to v2.0, CISO approval. |  |  |  | Open - owner review/approval required
6 | Succession Plan framework | Available - Staged (Needs Annual Review Stamp) | Review key leadership and critical technical roles for 2025-2026, re-stamp review date. |  |  |  | Open - owner review/approval required
7 | hiring procedure document/policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, confirm HR verification process. |  |  |  | Open - owner review/approval required
8 | Data capture policy/Data Collection Policy | Available - Staged (Needs Annual Review Stamp) | Update effective date to Oct 1, 2025, increment version to v2.0, management sign-off. |  |  |  | Open - owner review/approval required
9 | data transfer policy | Available - Staged (Needs Annual Review Stamp) | Update effective date to Oct 1, 2025, increment version to v2.0, confirm encryption standards in transit. |  |  |  | Open - owner review/approval required
10 | data usage policy | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
11 | whistle blowing policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, verify ombudsman / reporting contacts. |  |  |  | Open - owner review/approval required
12 | communication policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, verify internal/external notification matrix. |  |  |  | Open - owner review/approval required
13 | information security policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, formal CISO sign-off. |  |  |  | Open - owner review/approval required
14 | risk management policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, ensure methodology covers AI, Cloud, and Fraud risks. |  |  |  | Open - owner review/approval required
15 | accounting and financial operational procedures. | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, finance leadership approval. |  |  |  | Open - owner review/approval required
16 | Asset Management Policy | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
17 | fraud prevention policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, management approval sign-off. |  |  |  | Open - owner review/approval required
18 | 1) incident management policy 2) incident management response document | Available - Staged (Needs Annual Review Stamp) | Update effective date to Oct 1, 2025, verify incident response team (IRT) contact tree and escalation SLA. |  |  |  | Open - owner review/approval required
19 | policies and procedures for infrastructure deployment, development, approval. | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, ensure CI/CD code review, pull request approvals, and staging/prod separation are detailed. |  |  |  | Open - owner review/approval required
20 | Access management policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, confirm quarterly access review schedule and MFA requirements. |  |  |  | Open - owner review/approval required
21 | Password Management Policy | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
22 | Data retention and disposal policy. | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, verify retention schedules and NIST 800-88 sanitization standards. |  |  |  | Open - owner review/approval required
23 | data protection policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, management approval sign-off. |  |  |  | Open - owner review/approval required
24 | Removable media policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, verify policy prohibiting unencrypted USB/removable media. |  |  |  | Open - owner review/approval required
25 | software and infrastructure non-compliance monitoring policies and procedures. | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, align with cloud monitoring alerts. |  |  |  | Open - owner review/approval required
26 | policy for software installation. | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
27 | Antivirus and Malware prevention policy | Created & Staged (Ready for Annual Stamp) | Standalone policy extracted and generated. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
28 | Configuration management policy s | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, align with AWS baseline hardening. |  |  |  | Open - owner review/approval required
29 | Change Management policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, ensure emergency change workflow is clear. |  |  |  | Open - owner review/approval required
30 | Breach response and notification procedure | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, verify 72-hour regulatory notification SLA and client communication. |  |  |  | Open - owner review/approval required
31 | Business Continuity manual | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, verify RTO (<4 hours) and RPO (<1 hour) targets, update disaster contacts. |  |  |  | Open - owner review/approval required
32 | Development life cycle for continuous business development. | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, document CI/CD automated gates. |  |  |  | Open - owner review/approval required
33 | capacity management policy. | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, link with AWS auto-scaling and monitoring. |  |  |  | Open - owner review/approval required
34 | Physical Security Policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, verify visitor escort and clean desk rules. |  |  |  | Open - owner review/approval required
35 | Environmental Emergency Preparedness and Response procedure | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, update emergency assembly coordinates. |  |  |  | Open - owner review/approval required
36 | Backup and restoration procedure | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, specify AWS backup schedule, automated snapshots, and annual drill. |  |  |  | Open - owner review/approval required
37 | data storage policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, confirm AES-256 encryption at rest standards across databases and S3. |  |  |  | Open - owner review/approval required
38 | data privacy policy | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, bump version to v2.0, align with DPDP Act and GDPR criteria. |  |  |  | Open - owner review/approval required
39 | Remote working Policy | Created & Staged (Ready for Annual Stamp) | Comprehensive policy generated and staged. Review & confirm approval stamp for Oct 1, 2025 (v2.0). |  |  |  | Open - owner review/approval required
40 | Vulnerability Assessment and Penetration Testing Policy. | Available - Staged (Needs Annual Review Stamp) | Update review date to Oct 1, 2025, specify annual third-party VAPT mandate and remediation SLAs. |  |  |  | Open - owner review/approval required